## Plan Template Semester 2
|  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | CARNAVAL | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
|  |  |  | 10 Feb 2020 | [6 empty] | 17 Fed 2020 | [6 empty] | 24 Feb 2020 | [6 empty] | 2 Mar 2020 | [6 empty] | 9 Mar 2020 | [6 empty] | 16 Mar 2020 | [6 empty] | 23 Mar 2020
|  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TASK | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
PHASE 1 - ANALYSIS
Making groups of 4 members |  |  |  | M | T
Defining roles of group member | [5 empty] | W
Getting in touch with issue (e.g reader) |  |  |  |  | T | W | T | F | S | S
Coming up with Project Plan | [5 empty] | W
M1 - Meeting with client | [6 empty] | T
PHASE 2 - INVESTIGATION & DESIGN
Writing URS Document | [7 empty] | F | S | S | M
Defining IT solution | [7 empty] | F | S | S
Designing GUI (Website & Application) | [10 empty] | M | T | W | T
Identifying SQL data | [10 empty] | M | T | W | T
M2 - Meeting with client | [14 empty] | F
PHASE 3 - IMPLEMENTATION & TESTING
Review URS based on feedback | [14 empty] | F | S | S
Setting up SQL Database | [15 empty] | S | S
Making UI for application | [22 empty] | S | S | M | T
Making application UML | [24 empty] | M | T | W
M3 - Meeting with client | [27 empty] | T
Connecting application to SQL database | [27 empty] | T | F | S | S
Integrating UML to application | [27 empty] | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Integrating SQL Class into application | [27 empty] | T T: T; F F: F; S S: S; S S: S
Making HTML website | [31 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S
M4 - Meeting with client | bar: T
Connecting website to SQL database | [31 empty] | F: F; S: S; S: S; M: M; T: T; W: W
Create Test Plan | [31 empty] | F: F; S: S; S: S; M: M; T: T
Review Test Plan & write Test Report | [31 empty] | M: M; T: T; W: W; T: T; F: F; S: S; S: S
M5 - Meeting with client | bar: T
PHASE 5 - 'DEPLOYMENT' | bar: S to S
Commit final version to GIT | [45 empty] | M
Write Process Report | [45 empty] | M | T | W | T | bar: S to S
Present final product to client and peers | [45 empty] | M | T | W | T | F | S | S